## Weekly Report
|  |  |  | Shipment Preparation | [5 empty] | Form 4 | Clearance Process |  |  | Warehouse
|  |  |  | Supplier |  | Pick Up | Shipping |  |  |  | Clearance | NTRA | National Security | Gate in
|  |  |  | Readiness |  |  | Type | Dep. | ETA
Supplier | Invoice No. | Inv. Amount | Swift |  | Legalization
LG | 2012019-PI21-1 | 12250 | Done | Done | Done | Done |  | 2019-01-13 | 2019-03-04 | Done | 2019-03-12 | N.A | N.A | 2019-03-14
LG | 2012019-PI22-1 | 37800 | SO | [7 empty] | 12 Days
LG | 2012019-PI22-1 | 46200 | Waiting | [7 empty] | 12 Days
LG | 2012019-PI21-1 | 23600 | Waiting | Done | Done | Done |  | 2019-01-19 | 2019-03-06 | Done | 2019-03-19 | N.A | N.A | 2019-03-21
FAAC | 183000358 | 15737.2 | Waiting | Done | Done | Done |  | 2019-02-14 | 2019-02-24 | Done | 15 Days | N.A | Yes | 2019-03-26
GSL | 1000589 | 82034.14 | Done | Done | Waiting | 2019-03-02 |  | 2019-03-03 | 2019-03-06 | Done | 7 Days | 4 Days | N.A | 2019-03-17
SAMCOM | SAM/01258/2018 | 212644.29 | Done | Done | Done | 2019-01-10 |  | 2019-01-14 | 2019-02-14 | Done | 15 Days | 2019-03-16 | Done | 2019-03-21
SAMCOM | SAM/00016/2019 | 74677.51 | Waiting | Done | Done | Done |  | 2019-02-14 | 2019-03-07 | Done | 30 Days | 4 Days | 21 Days | 2019-03-28
SAMCOM | SAM/00016/2019 | 13700 | Waiting | Done | Done | Done |  | 2019-03-05 | 2019-03-07 | Waiting | 30 Days | 4 Days | 21 Days | 2019-04-06
SAMCOM | SAM/00016/2019 | 236251.86 | Waiting | Done | Done | Done |  | 2019-03-11 | 2019-04-01 | Waiting | 30 Days | 4 Days | 21 Days | 2019-05-01
RBH | * | 51537.5 | Waiting | Waiting Payment |  |  | Waiting |  |  |  | 7 Days | 4 Days | N.A
| Total Amount | 790695.3
15737.2
ETA: Estimated Time of Arrival
Dep. Departure date
All the Warehouse gate in dates are estimated according given dates
Highlighted Already Done
SO: Sales Order
Shipping Mode
Formulas:
Clearance Process = [ETA]+13
Warehouse = [ETA]+15
Warehouse = 4+7+[ETA]
ETA = [Dep.]+21